## WBS_Detailed_English
Task Mode | Task Name | Duration | Start | Finish | Predecessors | Resource Names
| Social Policy Support Chatbot | 66 days | 26/05/11 | 26/08/10 |  | Hung
| (Week 1-2): RAG/LLM Research & PDF Data Collection | 10 days | 26/05/11 | 26/05/22
| 1.1 Research RAG & LLM system knowledge | 5 days | 26/05/11 | 26/05/15 |  | Hung
| 1.2 Search and filter PDF documents | 10 days | 26/05/11 | 26/05/22 |  | Hung
| (Week 3-4): Build Data Pipeline & Retrieval | 10 days | 26/05/25 | 26/06/05 | 3
| 2.1 API-based OCR & Markdown Pre-processing | 10 days | 26/05/25 | 26/06/05 |  | Hung
| 2.2 Research and select Embedding Model | 5 days | 26/05/25 | 26/05/29 |  | Hung
| 2.3 Implement Chunking mechanism | 5 days | 26/06/01 | 26/06/05 | 8 | Hung
| 2.4 Research Vector DB & Deploy basic Retrieval flow | 5 days | 26/06/01 | 26/06/05 | 8 | Hung
| (Week 5-6): Integrate Gemini LLM & Process Table Structure | 10 days | 26/06/08 | 26/06/19 | 6
| 3.1 Integrate LLM API (Google Gemini) | 5 days | 26/06/08 | 26/06/12 |  | Hung
| 3.2 Optimize Chunking (Separate Text and Table flows) | 10 days | 26/06/08 | 26/06/19 |  | Hung
| 3.3 Develop system utility tools | 5 days | 26/06/15 | 26/06/19 | 12 | Hung
| (Week 7-8): Integrate Reranking, DB & Intent Router, Improve Input Data | 10 days | 26/06/22 | 26/07/03 | 11
| 4.1 Improve input data (Heading aware) | 5 days | 26/06/22 | 26/06/26 |  | Hung
| 4.2 Setup PostgreSQL, Redis & Reranking | 5 days | 26/06/22 | 26/06/26 |  | Hung
| 4.3 Build Intent Router (Lane routing) | 5 days | 26/06/29 | 26/07/03 | 16 | Hung
| 4.4 Develop Query Rewriter for follow-up questions | 5 days | 26/06/29 | 26/07/03 | 17 | Hung
| (Week 9-10): Create Dataset and Write Report | 10 days | 26/07/06 | 26/07/17 | 15
| 5.1 Pre-filter Metadata before vector search | 5 days | 26/07/06 | 26/07/10 |  | Hung
| 5.2 Create testing Dataset (Ground truth) | 5 days | 26/07/06 | 26/07/10 |  | Hung
| 5.3 Apply Gemini (Generator & Rewriter) | 5 days | 26/07/13 | 26/07/17 | 21 | Hung
| 5.4 Write Term Project Report (Draft 1) | 10 days | 26/07/06 | 26/07/17 |  | Hung
| (Week 11-12): Model Testing & Evaluation | 10 days | 26/07/20 | 26/07/31 | 20
| 6.1 Test Hit@k and Hit rate for Reranker | 5 days | 26/07/20 | 26/07/24 |  | Hung
| 6.2 Evaluate accuracy (LLM-as-a-judge) | 5 days | 26/07/27 | 26/07/31 | 26 | Hung
| (Buffer): Acceptance & Handover | 6 days | 26/08/03 | 26/08/10 | 25
| 7.1 Bug fixing & System optimization | 6 days | 26/08/03 | 26/08/10 |  | Hung
| 7.2 Acceptance & Finalize Report | 6 days | 26/08/03 | 26/08/10 |  | Hung